**Thesis writing plan**

*Final 3 weeks*

* Write physics motivation section at beginning of chapter 2 (1 day)
* Write physics motivation in opening paragraph (few hours)
* Restructure body chapters into cosmics data, x-ray data, comparison and edit (2 days)
* Implement Brigitte’s detailed edits (at least 1 week, 7 days)
* Three full read-throughs, ideally (at least 1 week, 7 days)
* Read through appendices again (1 day)
* Bib formatting (half day)
* Body formatting, eg. positioning figures (half day)
* Write abstract (half day)
* Acknowledgements and statement of contribution (few hours)

Today is Sept. 25.

No. days required: 19.5

No. workdays available: 15

* You’re working the next two weekends

Stay sane. Take care. God speed.

*Original*

To do

* Write chap 1, 2, 4, 5, 6
* Edit chap 1, 2, 4, 5, 6 🡪 Writing and editing chapters should take <1 week each, except introduction, < 2 weeks
* Get Brigitte’s feed back chap 1, 2, 3, 4, 5, 6 🡪 2 days for feedback implementation
* 2 full edits (full edit = 2 days)
* Brigitte full edit feedback ( 3 days)

Have: 10 weeks

* Writing: 5 weeks
* Full editing: 2 weeks

See Google calendar “thesis”